## 数据
project_id | project_name | project_type | customer_id | project_manager_employee_id | project_manager_name | team_size | planned_start_date | planned_end_date | actual_start_date | actual_end_date | forecast_end_date | contract_amount | budget_amount | actual_cost | recognized_revenue | collected_amount | outstanding_amount | budget_variance | project_status | highest_risk_level | acceptance_result | currency | source_type
P001 | 智慧园区 AI 数字人服务平台 | PTYPE-SMART-PARK | CUST001 | EMP0001 | 林澄（合成人员） | 14 | 2024-02-01 | 2024-10-31 | 2024-02-05 | 2024-10-28 |  | 3600000 | 3000000 | 2820000 | 3600000 | 3600000 | 0 | -180000 | completed | L2 | passed | CNY | SYNTHETIC_DERIVED
P002 | 银行企业知识助手项目 | PTYPE-KB-AGENT | CUST002 | EMP0002 | 周骁（合成人员） | 9 | 2024-03-01 | 2024-11-30 | 2024-03-11 | 2025-03-15 |  | 2800000 | 2200000 | 2650000 | 2520000 | 2520000 | 280000 | 450000 | completed_with_issues | L3 | passed_with_conditions | CNY | SYNTHETIC_DERIVED
P003 | 电力 AI 智能巡检平台 | PTYPE-VISION | CUST003 | EMP0003 | 顾川（合成人员） | 18 | 2024-05-01 | 2025-04-30 | 2024-05-08 | 2025-06-20 |  | 5800000 | 4900000 | 4860000 | 5800000 | 5800000 | 0 | -40000 | completed_with_issues | L4 | passed_with_conditions | CNY | SYNTHETIC_DERIVED
P004 | 制造企业知识库一期 | PTYPE-KB-AGENT | CUST004 | EMP0150 | 合成员工150 | 10 | 2025-01-01 | 2025-09-30 | 2025-01-06 | 2025-09-25 |  | 2400000 | 1980000 | 1910000 | 2400000 | 2160000 | 240000 | -70000 | completed | L1 | passed | CNY | SYNTHETIC
P005 | 城市服务智能客服平台 | PTYPE-AI-SOLUTION | CUST005 | EMP0142 | 合成员工142 | 12 | 2025-03-01 | 2025-12-31 | 2025-03-03 |  | 2026-12-31 | 3200000 | 2700000 | 1840000 | 1344000 | 1280000 | 1920000 | -860000 | delayed | L3 | not_started | CNY | SYNTHETIC
P006 | 产业园综合运营驾驶舱 | PTYPE-SMART-PARK | CUST006 | EMP0143 | 合成员工143 | 15 | 2025-05-01 | 2026-02-28 | 2025-05-08 |  | 2026-12-31 | 4500000 | 3820000 | 2380000 | 1890000 | 1800000 | 2700000 | -1440000 | delayed | L3 | not_started | CNY | SYNTHETIC
P007 | 教育机构数字人服务 | PTYPE-AI-SOLUTION | CUST007 | EMP0144 | 合成员工144 | 8 | 2025-07-01 | 2026-01-31 | 2025-07-02 |  | 2026-11-30 | 1680000 | 1390000 | 860000 | 705600 | 672000 | 1008000 | -530000 | delayed | L2 | not_started | CNY | SYNTHETIC
P008 | 交通场站视觉巡检 | PTYPE-VISION | CUST008 | EMP0145 | 合成员工145 | 13 | 2025-09-01 | 2026-08-31 | 2025-09-08 |  | 2026-11-30 | 3900000 | 3280000 | 1510000 | 1092000 | 780000 | 3120000 | -1770000 | delayed | L3 | not_started | CNY | SYNTHETIC
P009 | 零售知识助手试点 | PTYPE-KB-AGENT | CUST009 | EMP0180 | 合成员工180 | 6 | 2026-01-01 | 2026-06-30 | 2026-01-05 |  | 2026-10-31 | 980000 | 810000 | 420000 | 274400 | 196000 | 784000 | -390000 | delayed | L2 | not_started | CNY | SYNTHETIC
P010 | 政务热线智能体建设 | PTYPE-AI-SOLUTION | CUST010 | EMP0175 | 合成员工175 | 11 | 2026-02-01 | 2026-11-30 | 2026-02-09 |  |  | 3000000 | 2480000 | 870000 | 630000 | 600000 | 2400000 | -1610000 | in_progress | L2 | not_started | CNY | SYNTHETIC
P011 | 设备制造视觉质检 | PTYPE-VISION | CUST011 | EMP0148 | 合成员工148 | 14 | 2026-04-01 | 2027-03-31 | 2026-04-06 |  |  | 5200000 | 4400000 | 980000 | 728000 | 520000 | 4680000 | -3420000 | in_progress | L3 | not_started | CNY | SYNTHETIC
P012 | 集团知识平台升级 | PTYPE-KB-AGENT | CUST012 | EMP0149 | 合成员工149 | 9 | 2026-06-01 | 2027-01-31 | 2026-06-08 |  |  | 2100000 | 1720000 | 360000 | 294000 | 210000 | 1890000 | -1360000 | in_progress | L2 | not_started | CNY | SYNTHETIC

## 字段字典
field | type | description | allowed_values | entity_reference | required | confidentiality
project_id | string(id) | 项目稳定业务ID |  | DATA004.project_id | 是 | INTERNAL
project_name | string | project name |  |  | 按业务关系 | INTERNAL
project_type | string | project type |  |  | 按业务关系 | INTERNAL
customer_id | string(id) | 客户稳定业务ID |  | DATA002.customer_id | 按业务关系 | INTERNAL
project_manager_employee_id | string(id) | project manager employee id |  | DATA001.employee_id | 按业务关系 | INTERNAL
project_manager_name | string | project manager name |  |  | 按业务关系 | INTERNAL
team_size | number | team size |  |  | 按业务关系 | INTERNAL
planned_start_date | date | planned start date |  |  | 按业务关系 | INTERNAL
planned_end_date | date | planned end date |  |  | 按业务关系 | INTERNAL
actual_start_date | date | actual start date |  |  | 按业务关系 | INTERNAL
actual_end_date | date | actual end date |  |  | 按业务关系 | INTERNAL
forecast_end_date | date | 预测完成日期；延期项目填最新预测，按期或已完成项目留空 |  |  | 按业务关系 | INTERNAL
contract_amount | number | contract amount |  |  | 按业务关系 | INTERNAL
budget_amount | number | budget amount |  |  | 按业务关系 | INTERNAL
actual_cost | number | actual cost |  |  | 按业务关系 | INTERNAL
recognized_revenue | number | recognized revenue |  |  | 按业务关系 | INTERNAL
collected_amount | number | collected amount |  |  | 按业务关系 | INTERNAL
outstanding_amount | number | outstanding amount |  |  | 按业务关系 | INTERNAL
budget_variance | number | budget variance |  |  | 按业务关系 | INTERNAL
project_status | string | project status |  |  | 按业务关系 | INTERNAL
highest_risk_level | string | highest risk level | L1;L2;L3;L4 |  | 按业务关系 | INTERNAL
acceptance_result | string | acceptance result |  |  | 按业务关系 | INTERNAL
currency | string | 币种代码 | CNY |  | 是 | INTERNAL
source_type | string | 记录来源类型；SYNTHETIC为内部合成，SYNTHETIC_DERIVED为历史项目事实派生 | SYNTHETIC;SYNTHETIC_DERIVED |  | 是 | INTERNAL

## 元数据
dataset_id | DATA004
dataset_name | 项目主数据
dataset_type | project
filename | DATA004_结构化业务数据_项目主数据.xlsx
synthetic_notice | TRUE
source_authority | SYNTHETIC / SYNTHETIC_DERIVED
confidentiality | INTERNAL
as_of_date | 2026-09-12
record_count | 12
primary_key | project_id
company | 星澜数字科技有限公司（模拟企业）
usage_boundary | 仅用于模拟企业知识库；不得作为真实个人、客户或供应商数据使用