## 数据
contract_id | contract_type | project_id | customer_id | supplier_id | amount | currency | sign_date | start_date | end_date | payment_terms | owner_employee_id | contract_status | risk_level | source_type
P001-C01 | 销售合同 | P001 | CUST001 |  | 3600000 | CNY | 2024-01-22 | 2024-02-01 | 2024-10-31 | 30%预付款、40%上线、30%终验 | EMP0001 | completed | L1 | SYNTHETIC_DERIVED
P002-C01 | 销售合同 | P002 | CUST002 |  | 2800000 | CNY | 2024-02-26 | 2024-03-01 | 2025-03-15 | 20%预付款、30%试运行、50%终验；试运行付款证据定义不清 | EMP0002 | disputed | L3 | SYNTHETIC_DERIVED
P003-C01 | 销售合同 | P003 | CUST003 |  | 5800000 | CNY | 2024-04-15 | 2024-05-01 | 2025-06-20 | 20%预付款、30%设备到货、30%试运行、20%终验 | EMP0003 | completed | L2 | SYNTHETIC_DERIVED
PC-P001-01 | 采购合同 | P001 |  | SUP006 | 420000 | CNY | 2024-03-20 | 2024-03-20 | 2024-06-10 | 按到货与验收节点结算 | EMP0206 | completed | L1 | SYNTHETIC_DERIVED
PC-P002-01 | 采购合同 | P002 |  | SUP003 | 180000 | CNY | 2024-07-22 | 2024-07-22 | 2024-09-02 | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC_DERIVED
PC-P003-01 | 采购合同 | P003 |  | SUP001 | 1280000 | CNY | 2024-05-15 | 2024-05-15 | 2024-09-02 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC_DERIVED
PC-P003-02 | 采购合同 | P003 |  | SUP002 | 760000 | CNY | 2024-06-20 | 2024-06-20 | 2024-10-08 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC_DERIVED
PC005 | 采购合同 | P004 |  | SUP016 | 32000 | CNY | 2025-06-10 | 2025-06-10 | 2025-06-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC006 | 采购合同 | P005 |  | SUP019 | 68000 | CNY | 2025-07-10 | 2025-07-10 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
PC007 | 采购合同 | P006 |  | SUP022 | 128000 | CNY | 2026-01-10 | 2026-01-10 | 2026-01-28 | 按到货与验收节点结算 | EMP0206 | completed | L3 | SYNTHETIC
PC008 | 采购合同 | P007 |  | SUP025 | 260000 | CNY | 2025-09-10 | 2025-09-10 | 2025-09-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC009 | 采购合同 | P008 |  | SUP028 | 460000 | CNY | 2026-07-10 | 2026-07-10 | 2026-07-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC010 | 采购合同 | P009 |  | SUP001 | 920000 | CNY | 2026-03-10 | 2026-03-10 | 2026-03-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC011 | 采购合同 | P010 |  | SUP004 | 1150000 | CNY | 2026-08-10 | 2026-08-10 | 2026-08-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC012 | 采购合同 | P011 |  | SUP007 | 32000 | CNY | 2026-05-15 | 2026-05-15 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
PC013 | 采购合同 | P012 |  | SUP010 | 68000 | CNY | 2026-07-10 | 2026-07-10 | 2026-07-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC014 | 采购合同 | P004 |  | SUP013 | 128000 | CNY | 2025-03-10 | 2025-03-10 | 2025-03-28 | 按到货与验收节点结算 | EMP0206 | completed | L3 | SYNTHETIC
PC015 | 采购合同 | P005 |  | SUP016 | 260000 | CNY | 2026-04-10 | 2026-04-10 | 2026-04-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC016 | 采购合同 | P006 |  | SUP019 | 460000 | CNY | 2025-05-10 | 2025-05-10 | 2025-05-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC017 | 采购合同 | P007 |  | SUP022 | 920000 | CNY | 2026-06-10 | 2026-06-10 | 2026-06-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC018 | 采购合同 | P008 |  | SUP025 | 1150000 | CNY | 2025-10-15 | 2025-10-15 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
PC019 | 采购合同 | P009 |  | SUP028 | 32000 | CNY | 2026-08-10 | 2026-08-10 | 2026-08-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC020 | 采购合同 | P010 |  | SUP001 | 68000 | CNY | 2026-03-10 | 2026-03-10 | 2026-03-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC021 | 采购合同 | P011 |  | SUP004 | 128000 | CNY | 2026-08-25 | 2026-08-25 |  | 按到货与验收节点结算 | EMP0206 | active | L3 | SYNTHETIC
PC022 | 采购合同 | P012 |  | SUP007 | 260000 | CNY | 2026-07-15 | 2026-07-15 | 2026-08-05 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC023 | 采购合同 | P004 |  | SUP010 | 460000 | CNY | 2025-08-10 | 2025-08-10 | 2025-08-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC024 | 采购合同 | P005 |  | SUP013 | 920000 | CNY | 2025-04-15 | 2025-04-15 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
PC025 | 采购合同 | P006 |  | SUP016 | 1150000 | CNY | 2026-02-10 | 2026-02-10 | 2026-02-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC026 | 采购合同 | P007 |  | SUP019 | 32000 | CNY | 2025-08-10 | 2025-08-10 | 2025-08-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC027 | 采购合同 | P008 |  | SUP022 | 68000 | CNY | 2026-04-10 | 2026-04-10 | 2026-04-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC028 | 采购合同 | P009 |  | SUP025 | 128000 | CNY | 2026-02-10 | 2026-02-10 | 2026-02-28 | 按到货与验收节点结算 | EMP0206 | completed | L3 | SYNTHETIC
PC029 | 采购合同 | P010 |  | SUP028 | 260000 | CNY | 2026-06-10 | 2026-06-10 | 2026-06-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC030 | 采购合同 | P011 |  | SUP001 | 460000 | CNY | 2026-06-15 | 2026-06-15 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
PC031 | 采购合同 | P012 |  | SUP004 | 920000 | CNY | 2026-08-10 | 2026-08-10 | 2026-08-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC032 | 采购合同 | P004 |  | SUP007 | 1150000 | CNY | 2025-09-10 | 2025-09-10 | 2025-09-24 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC033 | 采购合同 | P005 |  | SUP010 | 32000 | CNY | 2026-08-20 | 2026-08-20 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
PC034 | 采购合同 | P006 |  | SUP013 | 68000 | CNY | 2025-11-10 | 2025-11-10 | 2025-11-28 | 按到货与验收节点结算 | EMP0206 | completed | L2 | SYNTHETIC
PC035 | 采购合同 | P007 |  | SUP016 | 128000 | CNY | 2026-08-15 | 2026-08-15 |  | 按到货与验收节点结算 | EMP0206 | active | L3 | SYNTHETIC
PC036 | 采购合同 | P008 |  | SUP019 | 260000 | CNY | 2025-11-15 | 2025-11-15 |  | 按到货与验收节点结算 | EMP0206 | active | L2 | SYNTHETIC
P004-C01 | 销售合同 | P004 | CUST004 |  | 2400000 | CNY | 2025-01-06 | 2025-01-01 | 2025-09-30 | 30%预付款、40%里程碑、30%验收 | EMP0150 | completed | L1 | SYNTHETIC
P005-C01 | 销售合同 | P005 | CUST005 |  | 3200000 | CNY | 2025-03-03 | 2025-03-01 | 2025-12-31 | 30%预付款、40%里程碑、30%验收 | EMP0142 | active | L2 | SYNTHETIC
P006-C01 | 销售合同 | P006 | CUST006 |  | 4500000 | CNY | 2025-05-08 | 2025-05-01 | 2026-02-28 | 30%预付款、40%里程碑、30%验收 | EMP0143 | active | L2 | SYNTHETIC
P007-C01 | 销售合同 | P007 | CUST007 |  | 1680000 | CNY | 2025-07-02 | 2025-07-01 | 2026-01-31 | 30%预付款、40%里程碑、30%验收 | EMP0144 | active | L1 | SYNTHETIC
P008-C01 | 销售合同 | P008 | CUST008 |  | 3900000 | CNY | 2025-09-08 | 2025-09-01 | 2026-08-31 | 30%预付款、40%里程碑、30%验收 | EMP0145 | active | L3 | SYNTHETIC
P009-C01 | 销售合同 | P009 | CUST009 |  | 980000 | CNY | 2026-01-05 | 2026-01-01 | 2026-06-30 | 30%预付款、40%里程碑、30%验收 | EMP0180 | active | L2 | SYNTHETIC
P010-C01 | 销售合同 | P010 | CUST010 |  | 3000000 | CNY | 2026-02-09 | 2026-02-01 | 2026-11-30 | 30%预付款、40%里程碑、30%验收 | EMP0175 | active | L2 | SYNTHETIC
P011-C01 | 销售合同 | P011 | CUST011 |  | 5200000 | CNY | 2026-04-06 | 2026-04-01 | 2027-03-31 | 30%预付款、40%里程碑、30%验收 | EMP0148 | active | L3 | SYNTHETIC
P012-C01 | 销售合同 | P012 | CUST012 |  | 2100000 | CNY | 2026-06-08 | 2026-06-01 | 2027-01-31 | 30%预付款、40%里程碑、30%验收 | EMP0149 | active | L2 | SYNTHETIC

## 字段字典
field | type | description | allowed_values | entity_reference | required | confidentiality
contract_id | string(id) | 合同稳定业务ID |  | DATA005.contract_id | 是 | HIGHLY_SENSITIVE
contract_type | string | contract type |  |  | 按业务关系 | HIGHLY_SENSITIVE
project_id | string(id) | 项目稳定业务ID |  | DATA004.project_id | 按业务关系 | HIGHLY_SENSITIVE
customer_id | string(id) | 客户稳定业务ID |  | DATA002.customer_id | 按业务关系 | HIGHLY_SENSITIVE
supplier_id | string(id) | 供应商稳定业务ID |  | DATA003.supplier_id | 按业务关系 | HIGHLY_SENSITIVE
amount | number | 金额，币种见currency |  |  | 按业务关系 | HIGHLY_SENSITIVE
currency | string | 币种代码 | CNY |  | 是 | HIGHLY_SENSITIVE
sign_date | date | sign date |  |  | 按业务关系 | HIGHLY_SENSITIVE
start_date | date | start date |  |  | 按业务关系 | HIGHLY_SENSITIVE
end_date | date | end date |  |  | 按业务关系 | HIGHLY_SENSITIVE
payment_terms | string | payment terms |  |  | 按业务关系 | HIGHLY_SENSITIVE
owner_employee_id | string(id) | owner employee id |  | DATA001.employee_id | 按业务关系 | HIGHLY_SENSITIVE
contract_status | string | contract status |  |  | 按业务关系 | HIGHLY_SENSITIVE
risk_level | string | risk level | L1;L2;L3;L4 |  | 按业务关系 | HIGHLY_SENSITIVE
source_type | string | 记录来源类型；SYNTHETIC为内部合成，SYNTHETIC_DERIVED为历史项目事实派生 | SYNTHETIC;SYNTHETIC_DERIVED |  | 是 | HIGHLY_SENSITIVE

## 元数据
dataset_id | DATA005
dataset_name | 合同台账
dataset_type | contract
filename | DATA005_结构化业务数据_合同台账.xlsx
synthetic_notice | TRUE
source_authority | SYNTHETIC / SYNTHETIC_DERIVED
confidentiality | HIGHLY_SENSITIVE
as_of_date | 2026-09-12
record_count | 48
primary_key | contract_id
company | 星澜数字科技有限公司（模拟企业）
usage_boundary | 仅用于模拟企业知识库；不得作为真实个人、客户或供应商数据使用