## 数据
procurement_id | project_id | supplier_id | purchase_contract_id | item_name | category | quantity | amount | method | request_date | delivery_date | committed_delivery_date | status | risk_level | source_type
PR-P001-01 | P001 | SUP006 | PC-P001-01 | 数字人渲染与园区展示设备 | 设备 | 1 | 420000 | 竞争性采购 | 2024-03-20 | 2024-06-10 | 2024-06-10 | completed | L1 | SYNTHETIC_DERIVED
PR-P002-01 | P002 | SUP003 | PC-P002-01 | 知识库测试环境资源 | 云服务 | 1 | 180000 | 三家比选 | 2024-07-22 | 2024-09-02 | 2024-08-15 | delayed | L2 | SYNTHETIC_DERIVED
PR-P003-01 | P003 | SUP001 | PC-P003-01 | GPU训练与推理服务器 | GPU与服务器 | 1 | 1280000 | 公开招标或专项审批 | 2024-05-15 | 2024-09-02 | 2024-08-20 | completed | L2 | SYNTHETIC_DERIVED
PR-P003-02 | P003 | SUP002 | PC-P003-02 | 视频采集与边缘计算设备 | 边缘设备 | 1 | 760000 | 竞争性采购 | 2024-06-20 | 2024-10-08 | 2024-10-08 | completed | L2 | SYNTHETIC_DERIVED
PR005 | P004 | SUP016 | PC005 | 办公设备采购5 | 办公设备 | 6 | 32000 | 简化采购 | 2025-06-10 | 2025-06-28 | 2025-06-28 | completed | L2 | SYNTHETIC
PR006 | P005 | SUP019 | PC006 | 网络设备采购6 | 网络设备 | 7 | 68000 | 三家比选 | 2025-07-10 |  | 2026-10-31 | approved | L2 | SYNTHETIC
PR007 | P006 | SUP022 | PC007 | 数据服务采购7 | 数据服务 | 8 | 128000 | 三家比选 | 2026-01-10 | 2026-01-28 | 2026-01-28 | completed | L3 | SYNTHETIC
PR008 | P007 | SUP025 | PC008 | GPU与服务器采购8 | GPU与服务器 | 1 | 260000 | 竞争性采购 | 2025-09-10 | 2025-09-28 | 2025-09-20 | completed | L2 | SYNTHETIC
PR009 | P008 | SUP028 | PC009 | 边缘设备采购9 | 边缘设备 | 2 | 460000 | 竞争性采购 | 2026-07-10 | 2026-07-28 | 2026-07-28 | completed | L2 | SYNTHETIC
PR010 | P009 | SUP001 | PC010 | 云服务采购10 | 云服务 | 3 | 920000 | 竞争性采购 | 2026-03-10 | 2026-03-28 | 2026-03-28 | completed | L2 | SYNTHETIC
PR011 | P010 | SUP004 | PC011 | 软件许可采购11 | 软件许可 | 4 | 1150000 | 公开招标或专项审批 | 2026-08-10 | 2026-08-28 | 2026-08-28 | completed | L2 | SYNTHETIC
PR012 | P011 | SUP007 | PC012 | 实施服务采购12 | 实施服务 | 5 | 32000 | 简化采购 | 2026-05-15 |  | 2026-12-31 | approved | L2 | SYNTHETIC
PR013 | P012 | SUP010 | PC013 | 办公设备采购13 | 办公设备 | 6 | 68000 | 三家比选 | 2026-07-10 | 2026-07-28 | 2026-07-28 | completed | L2 | SYNTHETIC
PR014 | P004 | SUP013 | PC014 | 网络设备采购14 | 网络设备 | 7 | 128000 | 三家比选 | 2025-03-10 | 2025-03-28 | 2025-03-28 | completed | L3 | SYNTHETIC
PR015 | P005 | SUP016 | PC015 | 数据服务采购15 | 数据服务 | 8 | 260000 | 竞争性采购 | 2026-04-10 | 2026-04-28 | 2026-04-20 | completed | L2 | SYNTHETIC
PR016 | P006 | SUP019 | PC016 | GPU与服务器采购16 | GPU与服务器 | 1 | 460000 | 竞争性采购 | 2025-05-10 | 2025-05-28 | 2025-05-28 | completed | L2 | SYNTHETIC
PR017 | P007 | SUP022 | PC017 | 边缘设备采购17 | 边缘设备 | 2 | 920000 | 竞争性采购 | 2026-06-10 | 2026-06-28 | 2026-06-28 | completed | L2 | SYNTHETIC
PR018 | P008 | SUP025 | PC018 | 云服务采购18 | 云服务 | 3 | 1150000 | 公开招标或专项审批 | 2025-10-15 |  | 2026-11-15 | approved | L2 | SYNTHETIC
PR019 | P009 | SUP028 | PC019 | 软件许可采购19 | 软件许可 | 4 | 32000 | 简化采购 | 2026-08-10 | 2026-08-28 | 2026-08-20 | completed | L2 | SYNTHETIC
PR020 | P010 | SUP001 | PC020 | 实施服务采购20 | 实施服务 | 5 | 68000 | 三家比选 | 2026-03-10 | 2026-03-28 | 2026-03-28 | completed | L2 | SYNTHETIC
PR021 | P011 | SUP004 | PC021 | 办公设备采购21 | 办公设备 | 6 | 128000 | 三家比选 | 2026-08-25 |  | 2026-10-28 | approved | L3 | SYNTHETIC
PR022 | P012 | SUP007 | PC022 | 网络设备采购22 | 网络设备 | 7 | 260000 | 竞争性采购 | 2026-07-15 | 2026-08-05 | 2026-08-05 | completed | L2 | SYNTHETIC
PR023 | P004 | SUP010 | PC023 | 数据服务采购23 | 数据服务 | 8 | 460000 | 竞争性采购 | 2025-08-10 | 2025-08-28 | 2025-08-28 | completed | L2 | SYNTHETIC
PR024 | P005 | SUP013 | PC024 | GPU与服务器采购24 | GPU与服务器 | 1 | 920000 | 竞争性采购 | 2025-04-15 |  | 2026-11-30 | approved | L2 | SYNTHETIC
PR025 | P006 | SUP016 | PC025 | 边缘设备采购25 | 边缘设备 | 2 | 1150000 | 公开招标或专项审批 | 2026-02-10 | 2026-02-28 | 2026-02-28 | completed | L2 | SYNTHETIC
PR026 | P007 | SUP019 | PC026 | 云服务采购26 | 云服务 | 3 | 32000 | 简化采购 | 2025-08-10 | 2025-08-28 | 2025-08-28 | completed | L2 | SYNTHETIC
PR027 | P008 | SUP022 | PC027 | 软件许可采购27 | 软件许可 | 4 | 68000 | 三家比选 | 2026-04-10 | 2026-04-28 | 2026-04-28 | completed | L2 | SYNTHETIC
PR028 | P009 | SUP025 | PC028 | 实施服务采购28 | 实施服务 | 5 | 128000 | 三家比选 | 2026-02-10 | 2026-02-28 | 2026-02-28 | completed | L3 | SYNTHETIC
PR029 | P010 | SUP028 | PC029 | 办公设备采购29 | 办公设备 | 6 | 260000 | 竞争性采购 | 2026-06-10 | 2026-06-28 | 2026-06-28 | completed | L2 | SYNTHETIC
PR030 | P011 | SUP001 | PC030 | 网络设备采购30 | 网络设备 | 7 | 460000 | 竞争性采购 | 2026-06-15 |  | 2027-01-31 | approved | L2 | SYNTHETIC
PR031 | P012 | SUP004 | PC031 | 数据服务采购31 | 数据服务 | 8 | 920000 | 竞争性采购 | 2026-08-10 | 2026-08-28 | 2026-08-28 | completed | L2 | SYNTHETIC
PR032 | P004 | SUP007 | PC032 | GPU与服务器采购32 | GPU与服务器 | 1 | 1150000 | 公开招标或专项审批 | 2025-09-10 | 2025-09-24 | 2025-09-24 | completed | L2 | SYNTHETIC
PR033 | P005 | SUP010 | PC033 | 边缘设备采购33 | 边缘设备 | 2 | 32000 | 简化采购 | 2026-08-20 |  | 2026-11-30 | approved | L2 | SYNTHETIC
PR034 | P006 | SUP013 | PC034 | 云服务采购34 | 云服务 | 3 | 68000 | 三家比选 | 2025-11-10 | 2025-11-28 | 2025-11-28 | completed | L2 | SYNTHETIC
PR035 | P007 | SUP016 | PC035 | 软件许可采购35 | 软件许可 | 4 | 128000 | 三家比选 | 2026-08-15 |  | 2026-11-15 | approved | L3 | SYNTHETIC
PR036 | P008 | SUP019 | PC036 | 实施服务采购36 | 实施服务 | 5 | 260000 | 竞争性采购 | 2025-11-15 |  | 2026-10-31 | approved | L2 | SYNTHETIC

## 字段字典
field | type | description | allowed_values | entity_reference | required | confidentiality
procurement_id | string(id) | 采购申请/订单稳定业务ID |  |  | 是 | SENSITIVE
project_id | string(id) | 项目稳定业务ID |  | DATA004.project_id | 按业务关系 | SENSITIVE
supplier_id | string(id) | 供应商稳定业务ID |  | DATA003.supplier_id | 按业务关系 | SENSITIVE
purchase_contract_id | string(id) | purchase contract id |  | DATA005.contract_id | 按业务关系 | SENSITIVE
item_name | string | item name |  |  | 按业务关系 | SENSITIVE
category | string | category |  |  | 按业务关系 | SENSITIVE
quantity | number | quantity |  |  | 按业务关系 | SENSITIVE
amount | number | 金额，币种见currency |  |  | 按业务关系 | SENSITIVE
method | string | method |  |  | 按业务关系 | SENSITIVE
request_date | date | request date |  |  | 按业务关系 | SENSITIVE
delivery_date | date | delivery date |  |  | 按业务关系 | SENSITIVE
committed_delivery_date | date | 承诺交付日期；供应商承诺的交付截止日 |  |  | 按业务关系 | SENSITIVE
status | string | status |  |  | 按业务关系 | SENSITIVE
risk_level | string | risk level | L1;L2;L3;L4 |  | 按业务关系 | SENSITIVE
source_type | string | 记录来源类型；SYNTHETIC为内部合成，SYNTHETIC_DERIVED为历史项目事实派生 | SYNTHETIC;SYNTHETIC_DERIVED |  | 是 | SENSITIVE

## 元数据
dataset_id | DATA006
dataset_name | 采购订单台账
dataset_type | procurement
filename | DATA006_结构化业务数据_采购订单台账.xlsx
synthetic_notice | TRUE
source_authority | SYNTHETIC / SYNTHETIC_DERIVED
confidentiality | SENSITIVE
as_of_date | 2026-09-12
record_count | 36
primary_key | procurement_id
company | 星澜数字科技有限公司（模拟企业）
usage_boundary | 仅用于模拟企业知识库；不得作为真实个人、客户或供应商数据使用